## SUB-L10
WBS_1 | WBS_2 | WBS_3 | WBS_4 | DESCRIPTION | UNIT | SUB | L1 | 1M | L2 | L3 | CM1A/B | CM2A/B | CM3A/B | CM4A/B | CM5A/B | CM6A/B | L4 | L4M | QTY | MAT. | LAB. | TOTAL | AMOUNT | Percent_Wt | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Piling | 1.00m dia. pile cut-off. | No. | 106 | [12 empty] | 106 | 335 | 1730 | 2065 | 218890 | 0.14916 | 50 | 50 | [10 empty] | 60 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Piling | 1.20m dia. pile cut-off. | No. | 70 | [12 empty] | 70 | 335 | 2120 | 2455 | 171850 | 0.1171 | 50 | 50 | [10 empty] | 60 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Piling | 1.50m dia. pile cut-off. | No. | 2 | [12 empty] | 2 | 450 | 3460 | 3910 | 7820 | 0.0053287 | 100 | [11 empty] | 100
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Piling | Pile head disposal, off-site. | No. | 178 | [12 empty] | 178 | 0 | 1325 | 1325 | 235850 | 0.16071 |  | 50 | 50 | [10 empty] | 60 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Excavation to footing | M3 | 15008 | [12 empty] | 15008 | 0 | 110 | 110 | 1650880 | 1.1249 |  |  |  | 40 | 60 | [8 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Remove excavation material, off-site | M3 | 6837 | [12 empty] | 6837 | 0 | 70 | 70 | 478590 | 0.32612 |  |  |  | 40 | 60 | [8 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Back fill by existing soil. | M3 | 8165 | [12 empty] | 8165 | 0 | 110 | 110 | 898150 | 0.61202 |  |  |  |  | 60 | 40 | [7 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Existing grade compaction | M2 | 0 | [12 empty] | 0 | 0 | 35 | 35 | 0 | 0 |  |  |  |  | 60 | 40 | [7 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Compacted sand, 50 100 mm thick | M2 | 82 | [12 empty] | 820 | 95 | 15 | 110 | 90200 | 0.061464 |  |  |  |  | 60 | 40 | [7 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Lean concrete, 50 100 mm thick | M2 | 82 | [12 empty] | 820 | 165 | 70 | 235 | 192700 | 0.13131 |  |  |  | 30 | 30 | 40 | [7 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Concrete 320ksc. cylinder test | M3 | 1858 | [12 empty] | 1858 | 1985 | 265 | 2250 | 4180500 | 2.8487 |  |  |  | 30 | 30 | 40 | [7 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Formworks | M2 | 1220 | [12 empty] | 1220 | 195 | 260 | 455 | 555100 | 0.37826 |  |  |  | 30 | 30 | 40 | [9 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Rebar SR24, 6mm dia. | KG. | 0 | [12 empty] | 0 | 24 | 5.5 | 29.5 | 0 | 0 |  |  |  | 30 | 30 | 40 | [9 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Rebar SR24, 9mm dia. | KG. | 0 | [12 empty] | 0 | 23 | 5.5 | 28.5 | 0 | 0 |  |  |  | 30 | 30 | 40 | [9 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Rebar SD40, 10mm dia. | KG. | 0 | [12 empty] | 0 | 23 | 5.5 | 28.5 | 0 | 0 |  |  |  | 30 | 30 | 40 | [9 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Rebar SD40, 12mm dia. | KG. | 279 | [12 empty] | 279 | 22.5 | 5 | 27.5 | 7672.5 | 0.0052282 |  |  |  | 30 | 30 | 40 | [9 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Rebar SD40, 16mm dia. | KG. | 27341 | [12 empty] | 27341 | 22 | 5 | 27 | 738207 | 0.50303 |  |  |  | 30 | 30 | 40 | [9 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Rebar SD50, 20mm dia. | KG. | 10179 | [12 empty] | 10179 | 22.5 | 4.5 | 27 | 274833 | 0.18728 |  |  |  | 30 | 30 | 40 | [9 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Rebar SD50, 25mm dia. | KG. | 89151 | [12 empty] | 89151 | 22.5 | 4.5 | 27 | 2407077 | 1.6402 |  |  |  | 30 | 30 | 40 | [9 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Rebar SD50, 28mm dia. | KG. | 178586 | [12 empty] | 178586 | 22.5 | 4.5 | 27 | 4821822 | 3.2857 |  |  |  | 30 | 30 | 40 | [9 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Rebar SD50, 32mm dia. | KG. | 108769 | [12 empty] | 108769 | 22.5 | 4.5 | 27 | 2936763 | 2.0012 |  |  |  | 30 | 30 | 40 | [9 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Standard Foundation [F1-F12] | Allow for Shear Key | KG. | 0 | [12 empty] | 0 | 24 | 5.5 | 29.5 | 0 | 0 |  |  |  | 30 | 30 | 40 | [9 empty] | 30 | 30 | 40
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Excavation to footing (Include in F1,F2) | M3 | 0 | [12 empty] | 0 | 0 | 110 | 110 | 0 | 0 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Remove excavation material, off-site (Include in F1,F2) | M3 | 0 | [12 empty] | 0 | 0 | 70 | 70 | 0 | 0 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Back fill by existing soil. (Include in F1,F2) | M3 | 0 | [12 empty] | 0 | 0 | 110 | 110 | 0 | 0 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Existing grade compaction | M2 | 0 | [12 empty] | 0 | 0 | 35 | 35 | 0 | 0 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Compacted sand, 50 100 mm thick | M2 | 400 | [12 empty] | 400 | 95 | 15 | 110 | 44000 | 0.029983 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Lean concrete, 50 100 mm thick | M2 | 400 | [12 empty] | 400 | 165 | 70 | 235 | 94000 | 0.064054 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Concrete 320ksc. cylinder test | M3 | 1077 | [12 empty] | 1077 | 1985 | 265 | 2250 | 2423250 | 1.6513 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Formworks | M2 | 228 | [12 empty] | 228 | 195 | 260 | 455 | 103740 | 0.070691 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Rebar SR24, 6mm dia. | KG. | 0 | [12 empty] | 0 | 24 | 5.5 | 29.5 | 0 | 0 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Rebar SR24, 9mm dia. | KG. | 0 | [12 empty] | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Rebar SD40, 10mm dia. | KG. | 0 | [12 empty] | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Rebar SD40, 12mm dia. | KG. | 0 | [12 empty] | 0 | 22.5 | 5 | 27.5 | 0 | 0 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Rebar SD40, 16mm dia. | KG. | 2035 | [12 empty] | 2035 | 22 | 5 | 27 | 54945 | 0.037441 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Rebar SD50, 20mm dia. | KG. | 0 | [12 empty] | 0 | 22.5 | 4.5 | 27 | 0 | 0 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Rebar SD50, 25mm dia. | KG. | 99696 | [12 empty] | 99696 | 22.5 | 4.5 | 27 | 2691792 | 1.8342 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Rebar SD50, 28mm dia. | KG. | 35411 | [12 empty] | 35411 | 22.5 | 4.5 | 27 | 956097 | 0.65151 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Rebar SD50, 32mm dia. | KG. | 0 | [12 empty] | 0 | 22.5 | 4.5 | 27 | 0 | 0 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Allow for Shear Key | KG. | 0 | [12 empty] | 0 | 24 | 5.5 | 29.5 | 0 | 0 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Mat Foundation [F66] | Curring concrete | M2 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 80 | 20 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | FOUNDATION | Soil slope stabilization | Allowance for temporary slope protection. | Item | 1 | [12 empty] | 1 | 14332500 | 0 | 14332500 | 14332500 | 9.7665 |  | 45 | 45 | [5 empty] | 10 |  |  |  |  | 80 | 10 |  |  |  | 10
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Reinforcement Concrete Wall [UGWx] | Concrete 320ksc. cylinder test ผสมน้ำยากันซึม | M3 | 229 | [12 empty] | 229 | 2060 | 265 | 2325 | 532425 | 0.36281 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Reinforcement Concrete Wall [UGWx] | Formworks | M2 | 1418 | [12 empty] | 1418 | 210 | 260 | 470 | 666460 | 0.45414 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Reinforcement Concrete Wall [UGWx] | Rebar SR24, 6mm dia. | Kg. | 0 | [12 empty] | 0 | 24 | 5.5 | 29.5 | 0 | 0 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Reinforcement Concrete Wall [UGWx] | Rebar SR24, 9mm dia. | Kg. | 1000 | [12 empty] | 1000 | 23 | 5.5 | 28.5 | 28500 | 0.019421 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Reinforcement Concrete Wall [UGWx] | Rebar SD40, 10mm dia. | Kg. | 0 | [12 empty] | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Reinforcement Concrete Wall [UGWx] | Rebar SD40, 12mm dia. | Kg. | 8918 | [12 empty] | 8918 | 22.5 | 5 | 27.5 | 245245 | 0.16712 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Reinforcement Concrete Wall [UGWx] | Rebar SD40, 16mm dia. | Kg. | 21407 | [12 empty] | 21407 | 22 | 5 | 27 | 577989 | 0.39385 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Reinforcement Concrete Wall [UGWx] | Rebar SD50, 20mm dia. | Kg. | 3901 | [12 empty] | 3901 | 22.5 | 4.5 | 27 | 105327 | 0.071772 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Reinforcement Concrete Wall [UGWx] | Rebar SD50, 25mm dia. | Kg. | 19819 | [12 empty] | 19819 | 22.5 | 4.5 | 27 | 535113 | 0.36464 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Reinforcement Concrete Wall [UGWx] | Rebar SD50, 28mm dia. | Kg. | 945 | [12 empty] | 945 | 22.5 | 4.5 | 27 | 25515 | 0.017386 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Reinforcement Concrete Wall [UGWx] | Rebar SD50, 32mm dia. | Kg. | 1115 | [12 empty] | 1115 | 22.5 | 4.5 | 27 | 30105 | 0.020514 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Water/Damp proof system | Waterproof membrane to external wall.(Bituthene 3000) | M2 | 605 | [12 empty] | 605 | 225 | 45 | 270 | 163350 | 0.11131 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Water/Damp proof system | Chemical coating to internal wall. (Include in Architects work) | M2 | 1130 | [12 empty] | 1130 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Water/Damp proof system | Water stop RX101-3/4" x 1" or Equivalent | M | 208 | [12 empty] | 208 | 235 | 145 | 380 | 79040 | 0.05386 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | BASEMENT WALL (EARTH RETAINING WALL) | Additional Items | Protection For Waterproof membrane to external wall. | M2 | 605 | [12 empty] | 605 | 140 | 190 | 330 | 199650 | 0.13605 | [6 empty] | 50 | 50 | [10 empty] | 80 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Excavation. | M3 | 0 | [12 empty] | 0 | 0 | 110 | 110 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [10 empty] | 30 | 80
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Remove excavation material, off-site | M3 | 0 | [12 empty] | 0 | 0 | 70 | 70 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Back fill by existing soil. | M3 | 0 | [12 empty] | 0 | 0 | 110 | 110 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Compacted soil | M2 | 0 | [12 empty] | 0 | 0 | 35 | 35 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Compacted sand, 50mm thick | M2 | 2 | [12 empty] | 2 | 95 | 15 | 110 | 220 | 0.00014991 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Lean concrete, 50mm thick | M2 | 2 | [12 empty] | 2 | 165 | 70 | 235 | 470 | 0.00032027 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Sheet membrane waterproof | M2 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Concrete 320ksc. cylinder test | M3 | 142 | [12 empty] | 142 | 1985 | 265 | 2250 | 319500 | 0.21771 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Formworks | M2 | 537 | [12 empty] | 537 | 195 | 260 | 455 | 244335 | 0.1665 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Rebar SR24, 6mm dia. | KG. | 0 | [12 empty] | 0 | 24 | 5.5 | 29.5 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Rebar SR24, 9mm dia. | KG. | 2183 | [12 empty] | 2183 | 23 | 5.5 | 28.5 | 62215.5 | 0.042395 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Rebar SD40, 10mm dia. | KG. | 0 | [12 empty] | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Rebar SD40, 12mm dia. | KG. | 6185 | [12 empty] | 6185 | 22.5 | 5 | 27.5 | 170087.5 | 0.1159 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Rebar SD40, 16mm dia. | KG. | 3781 | [12 empty] | 3781 | 22 | 5 | 27 | 102087 | 0.069564 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Rebar SD50, 20mm dia.(SD40) | KG. | 7905 | [12 empty] | 7905 | 22 | 4.5 | 26.5 | 209482.5 | 0.14275 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Rebar SD50, 25mm dia.(SD40) | KG. | 13417 | [12 empty] | 13417 | 22 | 4.5 | 26.5 | 355550.5 | 0.24228 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Rebar SD50, 28mm dia.(SD40) | KG. | 26520 | [12 empty] | 26520 | 22 | 4.5 | 26.5 | 702780 | 0.47889 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | STUB COLUMN & TIE BEAM | Reinforcement Concrete Beam | Rebar SD50, 32mm dia. | KG. | 10259 | [12 empty] | 10259 | 22.5 | 4.5 | 27 | 276993 | 0.18875 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Excavation to footing | M3 | 0 | [12 empty] | 0 | 0 | 110 | 110 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Remove excavation material, off-site | M3 | 0 | [12 empty] | 0 | 0 | 70 | 70 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Back fill by existing soil. | M3 | 0 | [12 empty] | 0 | 0 | 110 | 110 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Existing grade compaction | M2 | 0 | [12 empty] | 0 | 0 | 35 | 35 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Compacted sand, 50mm thick | M2 | 25 | [12 empty] | 25 | 95 | 15 | 110 | 2750 | 0.0018739 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Lean concrete, 50mm thick | M2 | 25 | [12 empty] | 25 | 165 | 70 | 235 | 5875 | 0.0040034 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Formworks | M2 | 534 | [12 empty] | 534 | 1575 | 220 | 1795 | 958530 | 0.65316 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Rebar SR24, 6mm dia. | Kg. | 0 | [12 empty] | 0 | 24 | 5.5 | 29.5 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Rebar SR24, 9mm dia. | Kg. | 0 | [12 empty] | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Rebar SD40, 10mm dia. | Kg. | 0 | [12 empty] | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Rebar SD40, 12mm dia. | Kg. | 0 | [12 empty] | 0 | 22.5 | 5 | 27.5 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Rebar SD40, 16mm dia. | Kg. | 36486 | [12 empty] | 36486 | 22 | 5 | 27 | 985122 | 0.67128 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Rebar SD50, 20mm dia.(SD40) | Kg. | 1132 | [12 empty] | 1132 | 22 | 4.5 | 26.5 | 29998 | 0.020441 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Rebar SD50, 25mm dia.(SD40) | Kg. | 0 | [12 empty] | 0 | 22 | 4.5 | 26.5 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Rebar SD50, 28mm dia.(SD40) | Kg. | 0 | [12 empty] | 0 | 22 | 4.5 | 26.5 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Compacted sand, 50mm thick | Rebar SD50, 32mm dia. | Kg. | 0 | [12 empty] | 0 | 22.5 | 4.5 | 27 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Water/Damp proof system | Sheet membrane waterproof (Bituthene 3000) | M2 | 470 | [12 empty] | 470 | 225 | 45 | 270 | 126900 | 0.086472 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Water/Damp proof system | Water Stope 8" | M | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Soil slope stabilization | Allowance for temporary slope protection. | Item | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Additional Items | Concrete 320ksc. cylinder test ผสมน้ำยากันซึม | M3 | 254 | [12 empty] | 254 | 2060 | 265 | 2325 | 590550 | 0.40241 | [5 empty] | 40 | 40 | 20 | [9 empty] | 30 | 30 | 20 | 20
STRUCTURE | SUBSTRUCTURE | LOWEST SLAB CONSTRUCTION | Additional Items | Waterproof (Internal) (Include in Architects work) | M2 | 940 | [12 empty] | 940 | 0 | 0 | 0 | 0 | 0
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Excavation. | M3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 115 | 0 | 0 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Remove excavation material, off-site | M3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 0 | 0 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Back fill by existing soil. | M3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 115 | 0 | 0 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Compacted soil | M2 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 0 | 40 | 40 | 8200 | 0.0055877 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Compacted sand, 50mm thick | M2 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 95 | 15 | 110 | 22550 | 0.015366 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Lean concrete, 50mm thick | M2 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 165 | 75 | 240 | 49200 | 0.033526 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Sheet membrane waterproof( PVC Sheet 0.15mm.) | M2 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 25 | 10 | 35 | 7175 | 0.0048892 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Concrete 320ksc. cylinder test | M3 | 0 | 151 | 121 | 175 | 12 | 8 | 8 | 8 | 8 | 8 | 8 | 407 | 9 | 923 | 1985 | 265 | 2250 | 2076750 | 1.4151 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Formworks | M2 | 0 | 760 | 686 | 733 | 93 | 57 | 57 | 57 | 57 | 57 | 57 | 1235 | 78 | 3927 | 195 | 260 | 455 | 1786785 | 1.2176 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Rebar SR24, 6mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 5.5 | 29.5 | 0 | 0 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Rebar SR24, 9mm dia. | KG. | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 23 | 5.5 | 28.5 | 1254 | 0.0008545 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Rebar SD40, 10mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Rebar SD40, 12mm dia. | KG. | 0 | 11486 | 9857 | 6291 | 1546 | 717 | 717 | 717 | 717 | 717 | 717 | 10075 | 1653 | 45210 | 22.5 | 5 | 27.5 | 1243275 | 0.8472 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Rebar SD40, 16mm dia. | KG. | 0 | 2686 | 4808 | 6003 | 219 | 95 | 95 | 95 | 95 | 95 | 95 | 34450 | 2212 | 50948 | 22 | 5 | 27 | 1375596 | 0.93736 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Rebar SD50, 20mm dia.(SD40) | KG. | 0 | 2140 | 7576 | 1390 | 495 | 402 | 402 | 402 | 402 | 402 | 402 | 14862 | 0 | 28875 | 22 | 4.5 | 26.5 | 765187.5 | 0.52142 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Rebar SD50, 25mm dia.(SD40) | KG. | 0 | 12347 | 11510 | 8402 | 1030 | 737 | 737 | 737 | 737 | 737 | 737 | 45623 | 0 | 83334 | 22 | 4.5 | 26.5 | 2208351 | 1.5048 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Rebar SD50, 28mm dia.(SD40) | KG. | 0 | 8787 | 0 | 21977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19444 | 0 | 50208 | 22 | 4.5 | 26.5 | 1330512 | 0.90664 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Reinforcement Concrete Beam | Rebar SD50, 32mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 4.5 | 27 | 0 | 0 | [7 empty] | 30 | 30 | 30 | 10
STRUCTURE | SUPERSTRUCTURE | BEAM | Post Tension Beam [PBxx] | Concrete 320ksc. cylinder test | M3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STRUCTURE | SUPERSTRUCTURE | BEAM | Post Tension Beam [PBxx] | Formworks | M2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STRUCTURE | SUPERSTRUCTURE | BEAM | Post Tension Beam [PBxx] | Rebar SR24, 6mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 5.5 | 29.5 | 0 | 0
STRUCTURE | SUPERSTRUCTURE | BEAM | Post Tension Beam [PBxx] | Rebar SR24, 9mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 5.5 | 28.5 | 0 | 0
STRUCTURE | SUPERSTRUCTURE | BEAM | Post Tension Beam [PBxx] | Rebar SD40, 10mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 5.5 | 28.5 | 0 | 0
STRUCTURE | SUPERSTRUCTURE | BEAM | Post Tension Beam [PBxx] | Rebar SD40, 12mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 5 | 27.5 | 0 | 0
STRUCTURE | SUPERSTRUCTURE | BEAM | Post Tension Beam [PBxx] | Rebar SD40, 16mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 5 | 27 | 0 | 0
STRUCTURE | SUPERSTRUCTURE | BEAM | Post Tension Beam [PBxx] | Rebar SD50, 20mm dia.(SD40) | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 4.5 | 26.5 | 0 | 0
STRUCTURE | SUPERSTRUCTURE | BEAM | Post Tension Beam [PBxx] | Rebar SD50, 25mm dia.(SD40) | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 4.5 | 26.5 | 0 | 0
STRUCTURE | SUPERSTRUCTURE | BEAM | Post Tension Beam [PBxx] | Rebar SD50, 28mm dia.(SD40) | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 4.5 | 26.5 | 0 | 0
STRUCTURE | SUPERSTRUCTURE | BEAM | Post Tension Beam [PBxx] | Rebar SD50, 32mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 4.5 | 27 | 0 | 0
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Excavation. | M3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 115 | 0 | 0 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Compacted soil | M2 | 0 | 2002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2002 | 0 | 40 | 40 | 80080 | 0.054568 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Compacted sand | M2 | 0 | 2002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2002 | 95 | 15 | 110 | 220220 | 0.15006 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Lean concrete, 30mm thick | M2 | 0 | 2002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2002 | 165 | 75 | 240 | 480480 | 0.32741 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Sheet membrane waterproof ( PVC Sheet 0.15mm.) | M2 | 0 | 2002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2002 | 25 | 10 | 35 | 70070 | 0.047747 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Concrete 320ksc. cylinder test, Waterproof Mix | M3 | 0 | 406 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 509 | 64 | 1115 | 2060 | 440 | 2500 | 2787500 | 1.8995 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Formworks | M2 | 0 | 412 | 882 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1722 | 289 | 3615 | 350 | 220 | 570 | 2060550 | 1.4041 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Rebar SR24, 6mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 5.5 | 29.5 | 0 | 0 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Rebar SR24, 9mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Rebar SD40, 10mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Rebar SD40, 12mm dia. | KG. | 0 | 12923 | 8563 | 5132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2421 | 6206 | 35245 | 22.5 | 5 | 27.5 | 969237.5 | 0.66046 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Rebar SD40, 16mm dia. | KG. | 0 | 45956 | 19539 | 3158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62691 | 336 | 131680 | 22 | 5 | 27 | 3555360 | 2.4227 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Rebar SD50, 20mm dia.(SD40) | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1731 | 0 | 1731 | 22 | 4.5 | 26.5 | 45871.5 | 0.031258 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Rebar SD50, 25mm dia.(SD40) | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4379 | 0 | 4379 | 22 | 4.5 | 26.5 | 116043.5 | 0.079075 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Rebar SD50, 28mm dia.(SD40) | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 4.5 | 26.5 | 0 | 0 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Reinforcement Concrete Slab | Rebar SD50, 32mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 4.5 | 27 | 0 | 0 | [8 empty] | 10 | 20 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | SLAB | Post-Tension Slab | Concrete 320ksc. cylinder test | M3 | 0 | 0 | 0 | 443 | 293 | 446 | 446 | 446 | 446 | 446 | 477 | 0 | 0 | 3443 | 2290 | 440 | 2730 | 9399390 | 6.405 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | SLAB | Post-Tension Slab | Formworks | M2 | 0 | 0 | 0 | 1808 | 1176 | 1766 | 1766 | 1766 | 1766 | 1766 | 1764 | 0 | 0 | 13578 | 350 | 220 | 570 | 7739460 | 5.2738 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | SLAB | Post-Tension Slab | Rebar SR24, 6mm dia. | Kg. | 0 | 0 | 0 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 0 | 0 | 232 | 24 | 5.5 | 29.5 | 6844 | 0.0046637 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | SLAB | Post-Tension Slab | Rebar SR24, 9mm dia. | Kg. | 0 | 0 | 0 | 694 | 381 | 728 | 728 | 728 | 728 | 728 | 728 | 0 | 0 | 5443 | 23 | 5.5 | 28.5 | 155125.5 | 0.10571 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | SLAB | Post-Tension Slab | Rebar SD40, 10mm dia. | Kg. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | SLAB | Post-Tension Slab | Rebar SD40, 12mm dia. | Kg. | 0 | 0 | 0 | 15028 | 11201 | 19726 | 19726 | 19726 | 19726 | 19726 | 20551 | 0 | 0 | 145410 | 22.5 | 5 | 27.5 | 3998775 | 2.7249 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | SLAB | Post-Tension Slab | Rebar SD40, 16mm dia. | Kg. | 0 | 0 | 0 | 5384 | 4999 | 6937 | 6937 | 6937 | 6937 | 6937 | 6937 | 0 | 0 | 52005 | 22 | 5 | 27 | 1404135 | 0.95681 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | SLAB | Post-Tension Slab | Rebar SD50, 20mm dia.(SD40) | Kg. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 4.5 | 26.5 | 0 | 0 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | SLAB | Post-Tension Slab | Rebar SD50, 25mm dia.(SD40) | Kg. | 0 | 0 | 0 | 2274 | 1583 | 2960 | 2960 | 2960 | 2960 | 2960 | 2960 | 0 | 0 | 21617 | 22 | 4.5 | 26.5 | 572850.5 | 0.39035 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | SLAB | Post-Tension Slab | Rebar SD50, 28mm dia.(SD40) | Kg. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 4.5 | 26.5 | 0 | 0 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | SLAB | Post-Tension Slab | Rebar SD50, 32mm dia. | Kg. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 4.5 | 27 | 0 | 0 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | SLAB | Post-Tension Slab | Post-tension slab & beam | M2 | 0 | 0 | 0 | 1626 | 1101 | 1648 | 1648 | 1648 | 1648 | 1648 | 1285 | 0 | 0 | 12252 | 500 | 0 | 500 | 6126000 | 4.1744 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | SLAB | Additional Items | Concrete 320ksc. cylinder test | M3 | 0 | 104 | 88 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 509 | 64 | 853 | 2060 | 440 | 2500 | 2132500 | 1.4531 | [9 empty] | 40 | 40 | 20
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Column [Cxx] | Concrete 500ksc. cylinder test | M3 | 0 | 210 | 248 | 118 | 111 | 107 | 76 | 92 | 107 | 86 | 168 | 118 | 118 | 1559 | 2520 | 265 | 2785 | 4341815 | 2.9586 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Column [Cxx] | Formworks | M2 | 0 | 750 | 894 | 430 | 396 | 383 | 284 | 329 | 383 | 306 | 565 | 425 | 425 | 5570 | 195 | 260 | 455 | 2534350 | 1.727 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Column [Cxx] | Rebar SR24, 6mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 5.5 | 29.5 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Column [Cxx] | Rebar SR24, 9mm dia. | KG. | 0 | 1876 | 2167 | 1086 | 1033 | 1029 | 883 | 931 | 960 | 888 | 1727 | 1067 | 1067 | 14714 | 23 | 5.5 | 28.5 | 419349 | 0.28575 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Column [Cxx] | Rebar SD40, 10mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Column [Cxx] | Rebar SD40, 12mm dia. | KG. | 0 | 4317 | 5120 | 2734 | 2453 | 2386 | 1960 | 2087 | 2468 | 1940 | 4158 | 2018 | 2018 | 33659 | 22.5 | 5 | 27.5 | 925622.5 | 0.63074 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Column [Cxx] | Rebar SD40, 16mm dia. | KG. | 0 | 3258 | 4013 | 1988 | 1616 | 1566 | 1298 | 1385 | 1566 | 1298 | 1897 | 3057 | 3057 | 25999 | 22 | 5 | 27 | 701973 | 0.47834 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Column [Cxx] | Rebar SD50, 20mm dia. | KG. | 0 | 5618 | 6470 | 4435 | 4937 | 4801 | 4031 | 4257 | 4801 | 4483 | 8606 | 5724 | 5724 | 63887 | 22.5 | 4.5 | 27 | 1724949 | 1.1754 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Column [Cxx] | Rebar SD50, 25mm dia. | KG. | 0 | 11006 | 12634 | 9508 | 9283 | 8994 | 7616 | 8021 | 8994 | 6896 | 12413 | 5408 | 5408 | 106181 | 22.5 | 4.5 | 27 | 2866887 | 1.9536 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Column [Cxx] | Rebar SD50, 28mm dia. | KG. | 0 | 22276 | 28130 | 10258 | 7489 | 7296 | 6201 | 6523 | 7296 | 6201 | 13218 | 12358 | 12358 | 139604 | 22.5 | 4.5 | 27 | 3769308 | 2.5685 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Column [Cxx] | Rebar SD50, 32mm dia. | KG. | 0 | 8827 | 10086 | 3448 | 3355 | 3271 | 2797 | 2937 | 3271 | 2797 | 8178 | 4447 | 4447 | 57861 | 22.5 | 4.5 | 27 | 1562247 | 1.0645 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Shear Wall [SWxx] | Concrete 500ksc. cylinder test | M3 | 0 | 171 | 202 | 86 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 94 | 94 | 1312 | 2520 | 265 | 2785 | 3653920 | 2.4899 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Shear Wall [SWxx] | Formworks | M2 | 0 | 1017 | 1187 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 561 | 561 | 7646 | 210 | 260 | 470 | 3593620 | 2.4488 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Shear Wall [SWxx] | Rebar SR24, 6mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 5.5 | 29.5 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Shear Wall [SWxx] | Rebar SR24, 9mm dia. | KG. | 0 | 1227 | 1430 | 688 | 614 | 614 | 614 | 614 | 614 | 614 | 614 | 622 | 622 | 8887 | 23 | 5.5 | 28.5 | 253279.5 | 0.17259 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Shear Wall [SWxx] | Rebar SD40, 10mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Shear Wall [SWxx] | Rebar SD40, 12mm dia. | KG. | 0 | 7074 | 8164 | 3928 | 3654 | 3654 | 3654 | 3654 | 3654 | 3654 | 3654 | 3918 | 3918 | 52580 | 22.5 | 5 | 27.5 | 1445950 | 0.9853 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Shear Wall [SWxx] | Rebar SD40, 16mm dia. | KG. | 0 | 3071 | 3549 | 1903 | 1787 | 1787 | 1787 | 1787 | 1787 | 1787 | 1787 | 2061 | 2061 | 25154 | 22 | 5 | 27 | 679158 | 0.46279 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Shear Wall [SWxx] | Rebar SD50, 20mm dia. | KG. | 0 | 5162 | 5966 | 2256 | 2252 | 2252 | 2252 | 2252 | 2252 | 2252 | 2252 | 2605 | 2605 | 34358 | 22.5 | 4.5 | 27 | 927666 | 0.63213 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Shear Wall [SWxx] | Rebar SD50, 25mm dia. | KG. | 0 | 13891 | 15917 | 6905 | 5951 | 5951 | 5951 | 5951 | 5951 | 5951 | 5951 | 5426 | 5426 | 89222 | 22.5 | 4.5 | 27 | 2408994 | 1.6415 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Shear Wall [SWxx] | Rebar SD50, 28mm dia. | KG. | 0 | 2911 | 2971 | 624 | 520 | 520 | 520 | 520 | 520 | 520 | 520 | 0 | 0 | 10146 | 22.5 | 4.5 | 27 | 273942 | 0.18667 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | COLUMN, LOAD BEARING & SHEAR WALL | Reinforcement Concrete Shear Wall [SWxx] | Rebar SD50, 32mm dia. | KG. | 0 | 813 | 912 | 540 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 465 | 465 | 5589 | 22.5 | 4.5 | 27 | 150903 | 0.10283 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Reinforcement Concrete Retaining Wall (WWAx) | Concrete 320ksc. cylinder test | M3 | [13 empty] | 0 | 2060 | 265 | 2325 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Reinforcement Concrete Retaining Wall (WWAx) | Formworks | M2 | [13 empty] | 0 | 210 | 260 | 470 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Reinforcement Concrete Retaining Wall (WWAx) | Rebar SR24, 6mm dia. | KG. | [13 empty] | 0 | 24 | 5.5 | 29.5 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Reinforcement Concrete Retaining Wall (WWAx) | Rebar SR24, 9mm dia. | KG. | [13 empty] | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Reinforcement Concrete Retaining Wall (WWAx) | Rebar SD40, 10mm dia. | KG. | [13 empty] | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Reinforcement Concrete Retaining Wall (WWAx) | Rebar SD40, 12mm dia. | KG. | [13 empty] | 0 | 22.5 | 5 | 27.5 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Reinforcement Concrete Retaining Wall (WWAx) | Rebar SD40, 16mm dia. | KG. | [13 empty] | 0 | 22 | 5 | 27 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Reinforcement Concrete Retaining Wall (WWAx) | Rebar SD50, 20mm dia. | KG. | [13 empty] | 0 | 22.5 | 4.5 | 27 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Reinforcement Concrete Retaining Wall (WWAx) | Rebar SD50, 25mm dia. | KG. | [13 empty] | 0 | 22.5 | 4.5 | 27 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Reinforcement Concrete Retaining Wall (WWAx) | Rebar SD50, 28mm dia. | KG. | [13 empty] | 0 | 22.5 | 4.5 | 27 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Reinforcement Concrete Retaining Wall (WWAx) | Rebar SD50, 32mm dia. | KG. | [13 empty] | 0 | 22.5 | 4.5 | 27 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Miscellaneous | Sheet membrane waterproof | M2 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | WATER RETAINING & NON LOAD BEARING WALL | Miscellaneous | Water Stope 8" | M | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 40 | 40 | 30
STRUCTURE | SUPERSTRUCTURE | STAIRCASE | Reinforcement Concrete Staircase [STxx] | Concrete 320ksc. cylinder test | M3 | 2 | 28 | 32 | 7 | 6 | 6 | 6 | 6 | 6 | 7 | 17 | 10 | 10 | 143 | 1985 | 550 | 2535 | 362505 | 0.24702 | [10 empty] | 20 | 80
STRUCTURE | SUPERSTRUCTURE | STAIRCASE | Reinforcement Concrete Staircase [STxx] | Formworks | M2 | 15 | 200 | 210 | 54 | 44 | 44 | 44 | 44 | 44 | 56 | 112 | 63 | 63 | 993 | 235 | 325 | 560 | 556080 | 0.37893 | [10 empty] | 20 | 80
STRUCTURE | SUPERSTRUCTURE | STAIRCASE | Reinforcement Concrete Staircase [STxx] | Stair_Rebar SR24, 6mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 5.5 | 29.5 | 0 | 0 | [10 empty] | 20 | 80
STRUCTURE | SUPERSTRUCTURE | STAIRCASE | Reinforcement Concrete Staircase [STxx] | Stair_Rebar SR24, 9mm dia. | KG. | 28 | 311 | 182 | 123 | 107 | 107 | 107 | 107 | 107 | 139 | 257 | 125 | 125 | 1825 | 23 | 5.5 | 28.5 | 52012.5 | 0.035442 | [10 empty] | 20 | 80
STRUCTURE | SUPERSTRUCTURE | STAIRCASE | Reinforcement Concrete Staircase [STxx] | Stair_Rebar SD40, 10mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 5.5 | 28.5 | 0 | 0 | [10 empty] | 20 | 80
STRUCTURE | SUPERSTRUCTURE | STAIRCASE | Reinforcement Concrete Staircase [STxx] | Stair_Rebar SD40, 12mm dia. | KG. | 84 | 1973 | 2542 | 650 | 537 | 537 | 537 | 537 | 537 | 662 | 1099 | 609 | 609 | 10913 | 22.5 | 5 | 27.5 | 300107.5 | 0.2045 | [10 empty] | 20 | 80
STRUCTURE | SUPERSTRUCTURE | STAIRCASE | Reinforcement Concrete Staircase [STxx] | Stair_Rebar SD40, 16mm dia. | KG. | 75 | 1650 | 1290 | 195 | 195 | 195 | 195 | 195 | 195 | 214 | 900 | 610 | 610 | 6519 | 22 | 5 | 27 | 176013 | 0.11994 | [10 empty] | 20 | 80
STRUCTURE | SUPERSTRUCTURE | STAIRCASE | Reinforcement Concrete Staircase [STxx] | Stair_Rebar SD50, 20mm dia.(SD40) | KG. | 0 | 52 | 601 | 57 | 57 | 57 | 57 | 57 | 57 | 75 | 127 | 68 | 68 | 1333 | 22 | 4.5 | 26.5 | 35324.5 | 0.024071 | [10 empty] | 20 | 80
STRUCTURE | SUPERSTRUCTURE | STAIRCASE | Reinforcement Concrete Staircase [STxx] | Stair_Rebar SD50, 25mm dia.(SD40) | KG. | 0 | 0 | 894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 894 | 22 | 4.5 | 26.5 | 23691 | 0.016144 | [10 empty] | 20 | 80
STRUCTURE | SUPERSTRUCTURE | STAIRCASE | Reinforcement Concrete Staircase [STxx] | Stair_Rebar SD50, 28mm dia.(SD40) | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 4.5 | 26.5 | 0 | 0 | [10 empty] | 20 | 80
STRUCTURE | SUPERSTRUCTURE | STAIRCASE | Reinforcement Concrete Staircase [STxx] | Stair_Rebar SD50, 32mm dia. | KG. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 4.5 | 27 | 0 | 0 | [10 empty] | 20 | 80
STRUCTURE | SUPERSTRUCTURE | ROOF FRAME | Additional Items | Allowance for Steel structure @ Canopy roof(Provisional) | Item |  |  | 1 | [10 empty] | 1 | 4000000 | 0 | 4000000 | 4000000 | 2.7257
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | WF-500x200x10x16 mm. (89.6 kg/m) | Kg | [13 empty] | 1290 | 64.5 | 22 | 86.5 | 111585 | 0.076036
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | WF-300x200x8x12 mm. (56.8 kg/m) | Kg | [13 empty] | 3120 | 64.5 | 22 | 86.5 | 269880 | 0.1839
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | WF-200x100x5.5x8 mm. (21.3 kg/m) | Kg | [13 empty] | 430 | 64.5 | 22 | 86.5 | 37195 | 0.025345
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | WF-150x75x5x7 mm. (14 kg/m) | Kg | [13 empty] | 420 | 64.5 | 22 | 86.5 | 36330 | 0.024756
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | PL-10 mm. (81 kg/m2) | Kg | [13 empty] | 1 | 56 | 22 | 78 | 78 | 5.3151e-05
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | PL-15 mm. (122 kg/m2) | Kg | [13 empty] | 100 | 56 | 22 | 78 | 7800 | 0.0053151
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | Dowel DB16 (L=1.80m) | Ea | [13 empty] | 6 | 87.5 | 65 | 152.5 | 915 | 0.0006235
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | Dowel DB12 (L=1.13m) | Ea | [13 empty] | 9 | 29.5 | 22 | 51.5 | 463.5 | 0.00031584
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | Antirust Paint | m2 | [13 empty] | 140 | 28 | 22 | 50 | 7000 | 0.00477
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | Enamel Paint | m2 | [13 empty] | 140 | 55.5 | 43.5 | 99 | 13860 | 0.0094445
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | Fireproof | m2 | [13 empty] | 140 | 175 | 43.5 | 218.5 | 30590 | 0.020845
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | Wire Brush | m2 | [13 empty] | 140 | 0 | 29 | 29 | 4060 | 0.0027666
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | Dia.60mm Stainless Coupler | ea | [13 empty] | 6 | 816.5 | 144 | 960.5 | 5763 | 0.003927
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | Dia.30mm Stainless Steel rod | m | [13 empty] | 140 | 1749 | 287.5 | 2036.5 | 285110 | 0.19428
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | 20mm.thk GMS Plate with Hole | ea | [13 empty] | 12 | 175 | 144 | 319 | 3828 | 0.0026085
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | Pin Dia.30mm | ea | [13 empty] | 12 | 350 | 287.5 | 637.5 | 7650 | 0.0052129
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Canopy | 10mm.thk Stainless Plate | ea | [13 empty] | 24 | 583 | 144 | 727 | 17448 | 0.011889
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Façade Support) | WF-300x150x5.5x8 mm. (32 kg/m) | Kg | [13 empty] | 4900 | 35 | 22 | 57 | 279300 | 0.19032
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Façade Support) | PL-12 mm. (97 kg/m2) | Kg | [13 empty] | 250 | 29.5 | 22 | 51.5 | 12875 | 0.0087733
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Façade Support) | Dowel DB16 (L=1.90m) | Ea | [13 empty] | 74 | 87.5 | 65 | 152.5 | 11285 | 0.0076898
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Façade Support) | Antirust Paint | m2 | [13 empty] | 190 | 28 | 22 | 50 | 9500 | 0.0064735
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Façade Support) | Enamel Paint | m2 | [13 empty] | 190 | 55.5 | 43.5 | 99 | 18810 | 0.012818
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Façade Support) | Fireproof | m2 | [13 empty] | 190 | 175 | 43.5 | 218.5 | 41515 | 0.028289
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Façade Support) | Wire Brush | m2 | [13 empty] | 190 | 0 | 29 | 29 | 5510 | 0.0037546
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Roof Stack | H-150x150x7x10 mm. (31.5 kg/m) | Kg | [13 empty] | 37590 | 35 | 22 | 57 | 2142630 | 1.46
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Roof Stack | WF-200x100x5.5x8 mm. (21.3 kg/m) | Kg | [13 empty] | 24300 | 35 | 22 | 57 | 1385100 | 0.94384
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Roof Stack | PL-25 mm. (203 kg/m2) | Kg | [13 empty] | 10100 | 30.5 | 22 | 52.5 | 530250 | 0.36132
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Roof Stack | PL-10 mm. (81 kg/m2) | Kg | [13 empty] | 6710 | 30.5 | 22 | 52.5 | 352275 | 0.24005
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Roof Stack | M16 J-Bolt | Ea | [13 empty] | 5300 | 82 | 45 | 127 | 673100 | 0.45867
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Roof Stack | Non Shrink Grout (3cm) | m2 | [13 empty] | 50 | 1224.5 | 647 | 1871.5 | 93575 | 0.063764
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Roof Stack | Antirust Paint | m2 | [13 empty] | 2170 | 28 | 22 | 50 | 108500 | 0.073934
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Roof Stack | Enamel Paint | m2 | [13 empty] | 2170 | 55.5 | 43.5 | 99 | 214830 | 0.14639
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Roof Stack | Fireproof | m2 | [13 empty] | 2170 | 175 | 72 | 247 | 535990 | 0.36524
STRUCTURE | SUPERSTRUCTURE | Steel Structure | Roof Stack | Wire Brush | m2 | [13 empty] | 2170 | 0 | 29 | 29 | 62930 | 0.042882
146751918.5